## Slide 1
A DEVELOPER'S WORKING MANUAL
SHOPPING MALL
DEVELOPMENT BLUEPRINT
From Groundbreaking to Grand Opening
A practical, end-to-end roadmap covering feasibility, land, design, statutory approvals, construction, leasing, operational readiness and commercial launch.
INDIA | INDICATIVE PROJECT FRAMEWORK | LOCAL VALIDATION REQUIRED

## Slide 2
What this blueprint is designed to do
A practical guide to the decisions, approvals and hand-offs that shape a mall project.
OVERVIEW
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
02
A developer's roadmap
• Translate an idea into a deliverable project
• Sequence decisions and workstreams
• Connect development, leasing and operations
A control framework
• Identify approvals and responsible authorities
• Track time, cost, risks and dependencies
• Create stage-gates before moving forward
A commercial plan
• Start leasing at the right stage
• Coordinate tenant requirements with design
• Prepare the mall for safe, legal opening
A shopping mall is not simply a building project. It is an integrated real-estate, retail, infrastructure and operating business that must be planned as one coordinated programme.

## Slide 3
The complete development journey
Eleven connected stages; several workstreams deliberately run in parallel.
LIFECYCLE
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
03
01 Concept & feasibility
• Indicative month 0–3
02 Land & due diligence
• Indicative month 1–6
03 Financial structuring
• Indicative month 3–8
04 Design & planning
• Indicative month 3–10
05 Approvals & clearances
• Indicative month 5–14
06 Pre-construction & tendering
• Indicative month 10–15
07 Construction & execution
• Indicative month 14–32
08 Leasing & commercialisation
• Indicative month 6–34
09 Fit-outs & pre-opening
• Indicative month 30–39
10 Final approvals & occupancy
• Indicative month 35–40
11 Launch & operations
• Indicative month 39–42
Typical overall duration: approximately 36–48 months, depending on site, scale, approvals, financing and market conditions.

## Slide 4
Indicative master project timeline
Overlapping workstreams are essential to delivering a mall efficiently.
TIMELINE
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
04
0
6
12
18
24
30
36
42
Concept & feasibility
Land & due diligence
Financial structuring
Design & planning
Government approvals
Pre-construction
Construction
Leasing
Fit-outs & pre-opening
Final approvals & occupancy
Launch & operations
Leasing begins early and runs in parallel with design and construction; it should not wait for building completion.

## Slide 5
Stages 1–2 | Concept, feasibility and land
Months 0–6 • Establish that the project is viable and the site is developable.
DEVELOPMENT
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
05
Stage 1 — Concept & feasibility
• Define positioning and target customer
• Study catchment, competition, spending and access
• Estimate demand, footfall and retail potential
• Set indicative GLA, category mix and project scale
• Prepare capex, revenue and return assumptions
Stage 2 — Land & due diligence
• Verify title, ownership chain, encumbrances and litigation
• Confirm zoning, permitted use and conversion requirements
• Check FSI/FAR, height, setbacks, access and easements
• Review utilities, flood risk and environmental constraints
• Obtain legal, survey and development-potential reports
Stage gate: proceed to major land commitment only when title, land use and development potential are satisfactorily established.

## Slide 6
Stage 3 | Financial planning and project structuring
Months 3–8 • Translate the concept into a fundable development plan.
DEVELOPMENT
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
06
Build the project cost
• Land and transaction costs
• Construction and infrastructure
• Professional and statutory fees
• Finance costs and contingencies
• Pre-opening and launch costs
Structure the funding
• Equity, debt, JV or institutional capital
• Drawdowns linked to milestones
• Working capital and liquidity buffers
• Funding conditions and financial closure
Test the business case
• Rental and occupancy assumptions
• Parking, advertising and ancillary income
• Operating costs and lifecycle capex
• Base, upside and downside scenarios
Key outputs: Detailed Project Report (DPR), cost plan, cash-flow schedule, funding plan and investment approval.

## Slide 7
Stage 4 | Design and planning
Months 3–10 • Integrate architecture, engineering, retail planning and operations.
DESIGN
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
07
Core professional team
• Master planner and mall architect
• Structural and MEP consultants
• HVAC, fire and life-safety specialists
• Traffic, vertical transportation and landscape consultants
• Project management, cost and sustainability consultants
Design decisions that shape performance
• GLA, circulation, visibility and tenant frontage
• Anchor locations, atriums and vertical movement
• Parking, loading, service corridors and back-of-house
• F&B exhaust, drainage, power and grease management
• Fire exits, evacuation, plant rooms and future flexibility
Design sequence: concept → schematic → design development → detailed engineering → coordinated good-for-construction drawings.

## Slide 8
Stage 5 | Government approvals and clearances
Months 5–14 and beyond • Create a site-specific approvals register.
APPROVALS
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
08
Approval area | Examples of approvals / compliance | Potential authority
Planning & building | Land use, layout / development permission, sanctioned plans, commencement, completion and occupancy | Planning / Development Authority; Municipal Corporation; Town Planning
Environment | Environmental clearance where applicable; pollution-control consents; STP and waste compliance | SEIAA / MoEFCC; State Pollution Control Board; local authority
Fire & life safety | Provisional design review / NOC, fire systems inspection and final clearance | State Fire Department / Chief Fire Officer
Utilities | Electricity, substation, water, sewer, lifts, escalators and electrical inspection | DISCOM; water/sewer utility; Electrical and Lift Inspectorates
Site-specific | Airport height, highway access, groundwater, CRZ, heritage, tree or forest permissions | AAI / highway authority / relevant bodies
Commercial operations | Shops & Establishments, trade permissions, F&B, cinema, signage and labour compliance | State Labour; local body; FSSAI; cinema / licensing authorities
Indicative only: applicability depends on plot, project size, facilities and current local law.

## Slide 9
How to manage statutory approvals
Treat approvals as a managed workstream—not last-minute paperwork.
APPROVALS
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
09
Create the register
• Approval name and legal basis
• Issuing authority and jurisdiction
• Documents, drawings and fees
• Submission, target and actual dates
• Validity, renewal and conditions
Assign accountability
• Developer's approval owner
• Architect / technical consultant
• Legal and liaison support
• Departmental contact and escalation
• Owner for every observation
Control dependencies
• Pre-application consultation
• Linked approvals and prerequisites
• Inspection and compliance evidence
• Conditions to close before next stage
• Renewals and ongoing obligations
An application acknowledgement or provisional NOC is not necessarily permission to build, occupy or open.

## Slide 10
Stage 6 | Tendering and pre-construction
Months 10–15 • Convert coordinated design into executable, cost-controlled packages.
EXECUTION
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
10
Commercial and technical preparation
• Freeze scope, drawings and specifications
• Prepare BOQs, tender packages and procurement plan
• Evaluate contractors on capability, price and delivery
• Finalise contracts, guarantees and insurance
• Approve baseline schedule and cost plan
Site mobilisation and controls
• Construction methodology and logistics plan
• Temporary utilities, site office and security
• Health, safety and environment plan
• Quality assurance and inspection plan
• Reporting cadence, change control and risk register
Stage gate: confirm applicable permissions, approved drawings, funding readiness and contractor mobilisation before relevant works begin.

## Slide 11
Stage 7 | Construction and project execution
Indicative period: Months 14–32 • Monitor delivery against an agreed baseline.
EXECUTION
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
11
Work package | Indicative months
Site preparation and excavation | 14–17
Piling and foundation | 16–20
Basements and parking structure | 18–24
Superstructure and slabs | 20–28
Building envelope and roofing | 25–31
MEP installation and services | 23–34
Internal works and common areas | 26–35
External development and landscaping | 28–33
Testing and commissioning | 33–37
Track schedule, cost, quality, procurement, safety, design changes, contractor productivity and statutory inspections.

## Slide 12
Stage 8 | Leasing and commercialisation
Begin early—once positioning, preliminary plans and commercial assumptions are credible.
LEASING
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
12
Indicative period | Leasing focus
Months 6–9 | Tenant mix, category strategy and leasing plans
Months 8–12 | Anchor tenant identification and negotiations
Months 10–18 | Anchor commitments and major brands
Months 15–25 | Fashion, lifestyle, electronics and other retailers
Months 18–28 | F&B, food court and entertainment
Months 24–34 | Specialty leasing, balance mix and final closures
Leasing must inform design
• Anchor requirements affect structure and services
• F&B needs exhaust, drainage, power and gas planning
• Cinema needs acoustics, structure and fire coordination
• Agree unit configuration and fit-out criteria early
• Track signed GLA and tenant opening commitments

## Slide 13
Stage 9 | Tenant fit-outs and pre-opening
Months 30–39 • Move from construction delivery to a coordinated retail opening.
READINESS
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
13
Tenant fit-out management
• Issue fit-out manual and technical guidelines
• Review and approve tenant drawings
• Hand over units against documented readiness criteria
• Inspect MEP, fire and life-safety installations
• Track snagging, rectification and opening commitments
Mall operational readiness
• Appoint mall leadership and operating teams
• Contract security, housekeeping and facility services
• Prepare SOPs, emergency plans and evacuation drills
• Commission BMS, lifts, escalators, HVAC and parking
• Train teams and test integrated operating procedures
Tenant possession, fit-out completion and permission to open to the public are separate milestones.

## Slide 14
Stage 10 | Completion, final approvals and occupancy
Indicative period: Months 35–40 • Physical completion alone does not authorise occupation.
REGULATORY GATE
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
14
Completion evidence
• Completion application and architect's certificate
• As-built drawings and sanctioned-plan conformity
• Structural stability certificate
• Final fire and life-safety evidence
• Electrical, lift and utility inspections
• Environmental and waste compliance, where applicable
Occupancy readiness
• Close authority observations and conditions
• Complete required inspections
• Obtain applicable Completion Certificate
• Obtain Occupancy Certificate from competent authority
• Confirm operational licences and tenant-level compliance
Part occupancy may be possible only where local rules allow and the area is independently safe, compliant and authorised.

## Slide 15
Stage 11 | Mall launch and commercial operations
Months 39–42 • Open only when legal, physical and operational readiness align.
OPENING
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
15
1. Integrated testing
• Systems, utilities, fire alarms, lifts, HVAC, BMS and emergency response
2. Soft opening
• Selected tenants, invited visitors, observation and issue closure
3. Public launch
• Marketing campaign, tenant coordination, customer services and traffic plan
4. Stabilisation
• Daily reviews, service recovery, tenant support and operating reports
5. 30 / 90-day reviews
• Footfall, sales indicators, occupancy, customer feedback and operating performance
A successful opening is the start of mall operations—not the end of the development process.

## Slide 16
Critical dependencies and stage gates
An upstream delay can affect design, approvals, construction, leasing and opening.
PROJECT CONTROL
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
16
Dependency / prerequisite | Decision or next milestone
Verified title + permitted land use | Investment / land commitment
Feasibility + development potential | Project positioning and design brief
Coordinated design + statutory submissions | Building permission pathway
Required permissions + pre-commencement conditions | Start of relevant construction works
Anchor tenant requirements | Final design and infrastructure coordination
Construction readiness + approved fit-out criteria | Tenant handover and fit-outs
Completion evidence + final clearances | Occupancy Certificate
Occupancy + operational licences | Public opening
Use formal stage-gate reviews; do not progress solely because a target date has arrived.

## Slide 17
Project governance | Who owns what?
One integrated team, with clear accountability and a single source of project truth.
GOVERNANCE
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
17
Role | Primary accountability
Developer / Promoter | Investment decisions, scope, risk appetite and project ownership
Project Director | Overall delivery, cross-functional coordination and escalation
Project Management Consultant | Schedule, cost, quality, reporting and change control
Architect / Consultants | Design integrity, technical coordination and statutory drawings
Legal / Liaison team | Land due diligence, contracts and approval coordination
Main Contractor | Construction execution, safety, quality and site delivery
Leasing Head | Tenant strategy, negotiations, documentation and leasing milestones
Mall Operations Head | Operating model, SOPs, staffing and readiness
Marketing Head | Positioning, launch plan, events and customer acquisition
Finance Head | Budget, cash flow, funding, controls and commercial reporting

## Slide 18
The developer's project dashboard
Review leading indicators weekly and at every formal stage gate.
GOVERNANCE
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
18
Dashboard area | What to monitor
Schedule | Planned vs actual progress; critical-path slippage; milestone forecast
Approvals | Submitted, approved, pending observations, conditions and expiry dates
Cost & cash | Committed cost, actual spend, forecast at completion and cash flow
Construction | Package progress, quality issues, safety, procurement and defects
Leasing | Signed GLA, occupancy pipeline, anchor status and tenant opening dates
Fit-outs | Units handed over, drawings approved, work progress and snags
Readiness | Systems commissioned, staff trained, vendors appointed and drills completed
Risk | Top risks, owner, mitigation, due date and escalation

## Slide 19
Common risks—and how to reduce them
Preventable issues are best addressed before they become critical-path delays.
RISK
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
19
Risk | Preventive action
Land title / land-use uncertainty | Independent legal and planning due diligence before commitment
Delayed statutory approvals | Approval matrix, early consultations and complete submissions
Design changes during construction | Coordinated design freeze and formal change control
Cost escalation | Detailed BOQs, contingency, procurement strategy and cost reporting
Late anchor commitments | Early anchor strategy and structured leasing pipeline
Utility capacity shortfall | Confirm demand and capacity with providers at concept stage
Tenant fit-out delays | Early fit-out manual, handover criteria and progress reviews
Occupancy / opening delay | Maintain sanctioned-plan compliance and close conditions progressively

## Slide 20
First 100 days | Mobilise the project
A practical start-up plan for a developer moving from idea to a structured project.
ACTION PLAN
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
20
Period | Priority actions
Days 1–15 | Define vision, target market, location and development objectives
Days 16–30 | Start land due diligence; appoint feasibility and legal support
Days 31–45 | Undertake catchment, competition and demand assessment
Days 46–60 | Confirm zoning, land use, FSI/FAR and development potential
Days 61–75 | Prepare concept plan, indicative GLA and preliminary financial model
Days 76–90 | Appoint architect, key consultants and project management support
Days 91–100 | Create approval matrix, master schedule, budget and governance structure
The 100-day plan is a mobilisation framework—not a substitute for statutory approvals.

## Slide 21
Project documentation | Build the audit trail
Maintain controlled, current records from land acquisition through operations.
DOCUMENT CONTROL
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
21
Record group | Documents to retain
Land & legal | Title deeds, search report, survey, zoning, land-use and development rights
Feasibility & finance | Market study, catchment report, DPR, cost plan, cash flow and funding documents
Design | Concept, sanctioned and GFC drawings, calculations, specifications and revisions
Approvals | Applications, acknowledgements, NOCs, permissions, conditions and correspondence
Construction | Contracts, BOQs, work orders, inspection reports, test certificates and as-builts
Leasing & fit-outs | Leasing plans, LOIs, agreements, fit-out manual, approved drawings and handover records
Operations & opening | SOPs, vendor SLAs, training, emergency plans, completion evidence and OC

## Slide 22
Important | Adapt the blueprint to the actual jurisdiction
The framework is India-oriented, but statutory requirements are site- and project-specific.
IMPORTANT
SHOPPING MALL DEVELOPMENT BLUEPRINT | INDIA
22
What must be verified
• State and local development control regulations
• Competent planning and building authority
• Project size, use, height and built-up area thresholds
• Environmental and pollution-control applicability
• Fire, utility and special-site clearances
• Conditions attached to each permission
What must not be assumed
• One approval list applies across all Indian cities
• An application acknowledgement is an approval
• Provisional fire clearance is final clearance
• Building completion automatically means occupancy
• Mall owner licences cover every tenant
• A target timeline guarantees authority processing
Before execution, obtain a project-specific legal and statutory opinion and confirm current rules with competent authorities.

## Slide 23
THE DEVELOPMENT PRINCIPLE
Plan right.
Build right. Open right.
A successful shopping mall is created when land, design, approvals, construction, leasing and operations move forward as one integrated programme.
SHOPPING MALL DEVELOPMENT BLUEPRINT | FROM CONCEPT TO COMMERCIAL OPERATIONS